## Risk Register
Risk Register Template
Program/Project Name: |  | Alton Teaches LLC
Date of Review |  | 2022-02-20
Risk Identification | [6 empty] | Risk Response |  |  | Risk Status
Risk ID | Date Identified | Risk Category | Risk Description | Probability | Impact | Risk Score | Response Category | Response Details | Owner & Ownership | Risk Status | Probable Impact Date | Mitigation Status Update | Target/Actual Resolution Date
1 | 2022-02-15 | Information Security | If our unpatched and outdated IT systems are not updated, we are at risk of operating system vulnerabilities being exploited. | 2 | 3 | 6 | Mitigate | Implement a bi-weekly software updating and patching process. | IT Operations Manager | Open | 2022-03-01 | Risk identified and opened | 2022-03-30
2 | 2021-01-08 | Technology | Due to COVID-19 and our employees working from home, a strain on our VPN server is causing slow network speeds, and an inability to get work done. | 3 | 3 | 9 | Mitigate | Upgrade our VPN server and bandwidth to support all employees working from home. | IT Operations Manager | Closed | 2021-01-08 | VPN server was successfully updated, now supports more bandwidth, and has eliminated VPN-related user issues. | 2021-01-31
3 | 2021-11-01 | Resource | Due to technical integration issues and not having enough develoeprs to support our IT modernization project, the project is currently 90 days behind schedule. | 3 | 1 | 3 | Mitigate | Request an additional developer from IT manager. | IT Modernization Project Manager | Issue | 2021-11-01 | Due to a lack of departmental resources, the department is unable to reallocate an additional person to the project team. | 2022-01-01
4 | [5 empty] | 0
5 | [5 empty] | 0
6 | [5 empty] | 0
7 | [5 empty] | 0
8 | [5 empty] | 0
9
10 | [5 empty] | 0

## Scale (hidden)
Risk Register Scale
Impact | High (3) | 3 | 6 | 9
| Moderate (3) | 2 | 4 | 6
| Minor (1) | 1 | 2 | 3
|  | Low (1) | Moderate (2) | High (3)
Probability

## Lists (hidden)
Status | Risk Category | Probability | Impact | Mitigation Approach
Open | Budget | 1 | 1 | Avoidance
Issue | Information Security | 2 | 2 | Transference
Closed | Operational | 3 | 3 | Mitigate
| Organizational |  |  | Acceptance
Regulatory
Resource
Schedule
Strategic
Supply Chain
Technology